## Summary-GroupIterationProgress
1
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 5.8 - 5.15 | Team formation, set up weekly meeting, Agree on deliver Notification Microservice, set up code review rule, brainstorm features | Github code merge issue: some of our team member face git authorization issue | The group need to assign specific task to specific person,avoid last-minute incomplete assignments | List detailed tasks and make sure each member understand their task and complete before the soft group deadline. | 1 | 0 | 2 | 1 | 1 | 36 | 33 | 3 | 5 | 8.5 | 4.5 | 0 | 0 | 11 | 4
1 | 5.16 - 5.28 | Jordany built out Springboot code, user stories discused and PivotalTracker implemented | Determining best platform to use, | fostering collaboration among development, and operational, and testing Unanticipated delays and costs related to scaling microservice | lack of effective communication and alignment. We need to ensure we have buy-in for process improvement. Misalignment between improvements and goals: Need to understand business objectives. | 10 | 10 | 3 | 2 | 1 | 68 | 44.5 | 5 | 16 | 7.5 | 9 | 8.5 | 5.5 | 9.5 | 2
2 | 5.29 - 6.11
3 | 6.12 - 6.18

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Jim Penner | Meeting Minutes, Glossary, References, and Risk Mgmt |  |  |  |  | Began sample code, including
Shenxiao(Sherry) Li | Mgr Plan-0 & Weekly Meeting
Chaozheng Zhu | Configration Plan-0
Hunter Washburne | Testing and QA Plan - 0
Jordany Arnaud | Proposal & Implement Plan - 0

## Jim Penner
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8.5 | 6.5 | 2 | 0 - Learning GIT, and refreshing Design Patterns, 1- During meetings, 2 - did up sample codes 5 - Meetings, and also main presentation, 6 - inputs into Moday.com and discord, | 0.5 | 1 | 1.5 | 0 | 0 | 3.5 | 2 |  | 1. Build some sample code;2. Did Team presentation 3. Risk Management doc 4. 1. Part of SPPP, Glossary and References | Not familiar with Springboot, and also need refresher on JUnit5, and RESTAssurance - not familiar with PivotalTracker | Need to skill up on PivotalTracker, catch up on lectures - Will we need a UML, or class diagram? | 1. Begin coding, 2. Testing, 3 2+ meetings, and discussion around next steps | 11
2 | 05/17-05/31 | 15 | 12.5 | 2.5 | 0 - Learning Spring Boot, RabbitMQ, Docker, | 5 | 2.5 | 3 | 0.5 | 0.5 | 1.5 | 2 |  | 1. Completed Spring boot Java program for Notification management, and RabbitMQ
1. Requirement analysis on UML
2. Design work on UML, and Design pattern: Observer
3. Work on Java code and RabbitMQ
4. Test, reading on various testing methods (auto/manual etc)and test connection of rabbitmQ and docker
6. Discussion on this during meetings
5. Regular meetings, discord, one one one, and emails

## Shenxiao(Sherry) Li
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10.5 | 7.5 | 3 | 0 - learn setup ssh in github and learn pivotal tracker, read several tutorials 1 - define high level requirements, 5 - make project plan & mgr plan, send reminders to team members 5- participate team meetings 6 - set up git, work on lab1 7 - research similar products, prepare presentation | 2 | 1 | 0 | 0 | 0 | 2 | 1.5 | 1 | 1. Write 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with SpringBoot framework, hard to write any code on it 2.Task assignments is not clear. | 1. finish SpringBoot tutorial in 2 weeks,set up Springboot environment 3.Write User Stories4. Send task assignments to all members again | 0 - continue to learn SpringBoot 1 - continue to define requirements 2- design users stories and start to define the logic and implement | 9h
| 05/17-05/29 | 21 | 18 | 3 | 0 - learn Springboot, RabbitMQ 1 - create user stories, define high level requirements for notification service 3.implement simple notification service code(springboot & rabbitmq) 5 - make project plan & mgr plan, send reminders to team members 5- participate team meetings 6 - set up & troubleshooting springboot and rabbitmq config 7.presentation for basic notification service | 8 | 1 | 0 | 5 | 0 | 3 | 5 | 1 | write simple/basic notification service under branch notification_service; fix build.gradle issue under branch fix_gradle; make presentation for current basic notification service | not fimilar with springboot; configurtion incompatible | Continue learn and practice in Springboot; make sure pivotaltracker is correctly record for each iteration; focus on key features | 10 | 10

## Chaozheng Zhu
Week # | The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles:
| Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
| 1 | 05/10-05/16 | 8 | 6 | 2 | 0 - learn git CD/CI, workflow and pivotal tracker 1 - define user story 5 - Teach teammates who unfamiliar github to go through whole push merge process 5 - make meeting minute and meeting agenda 5- Join team meetings 6 - set up git work flow standard 7 - On youtoube search for project samples | 1 | 0.5 | 0 | 0 | 0 | 4 | 3 | 1 | 1.Build configuration part of the SPPP 2.Set up git flow standard, helping teammates to go through 3. Find similar project on youtoube and github 4. taking meeting minute and agenda for second meeting | Learning CD/CI which is new concept for me defining more user stories to make our project more informative | already learn through youtoube and try set up in this week | CD CI Set up whole team start set up the frame work and UML class chart Each person has his own part start coding | 12
| 2 | 05/17-05/29 | 17 | 14 | 3 | 0 - learning springboots, CI workflow 1 - analysis requirement of notification and user management 2.design simple UI for team logic notification 3.implement springboots, set up database 5 - make the whole process requirement for github upload and download, align with all team members 5- participate team meetings 6 - set up CI for the project 7- organize all file and upload to github | 4 | 1 | 2 | 4 | 0 | 4 | 1 | 1 | 1.Designed UI for the logic of our notification service, give team material to discuss service logic 2. set up CI for project 3. help team organize github branches, merge essential functions on main branch 4. check required documents and upload to github as time required | Tried pretty long time to set up the springboots project, how align other code as well as set up database, mysql some new version do not support mac, so had go back and force to make it works | Continue learn and practice in Springboot; make sure pivotaltracker is correctly record for each iteration; focus on key features | get detail notification works in code, also clearify the logic of service with whole team | 14

## Jordany Arnaud
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design & Implementation Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 10 | 9 | 1 | 0 - Learn how to set up Git Credentials Manager for GitHub. 1 - Defined the project description and features. 2 - Discussed a design proposal with the team. 5 - Participated in team meetings and group chat discussions. 6 - Set up Git. 7 - Conducted research. | 0.5 | 3 | 2 | 0 | 0 | 0.5 | 1 | 2 | 1 - Git / GitHub setup 2 - Worked on the project overview and high-level requirements for the SPPP document, defining the features for the application and create user stories 3 - Participated in the team's meeting and discussion. 4 - Researched cloud solutions for deployment. | 1- Difficulty coordinating with other teams due to different availability slots. 2- GitHub push issue because the account has not joined the project. 3- Not familiar with Pivotal Tracker. | 1- Finally, we have come to an agreement about which service each team is offering. 2- GitHub issue fixed and setup completed. 3- The plan is to learn Pivotal Tracker. | 0 - Continue learning Pivotal Tracker. 1 - Work on the design document and the API specification. 3 - Create the project structure and begin implementation. | 15h
2 | 05/16-05/21 | 21 | 18 | 3 | 0-Learned how to configure Auth0 for API security. 1-Defined the scope of user management services in terms of the features we can offer. 2-Designed and documented the overall architecture. 3-Created a Spring Boot project for the user management service with a proposed project structure. 5-Actively participated in most meetings, engaging in discussions, and remained responsive in group chats. 6-Configured Auth0 for the user management service and provided a demo to the team. | 2 | 2 | 2 | 3 | 1 | 4 | 4 | 0 | 1-Set up and configured Auth0 for the user management service. 2-Created a Spring Boot API project for the user management service. 3-Tested the security configuration to ensure its effectiveness. 4-Completed the sections on Introduction and Software Architecture in the SDD document. | 1-Encountered difficulty with the Auth0 configuration. 2-Encountered difficulty in finding a free database instance. 3-Encountered difficulty in keeping up with other teams regarding security measures. | 1-Sorted out the Auth0 configuration after spending some time on it. 2-Finally found a free database instance online. 3-Still need to follow up with the other teams regarding security. | 1- Plan to completed the security section in the SDD document. 2- Plan to completed the database and security configurations for the user management service. | 20
3 | 05/22-05/28 | 22 | 19 | 3 | 0-Learned how to secure OAuth2 with Auth0 in a Spring Boot application. 2-Prepared the flow diagram for security and implemented security measures in the user management service. 3-Implemented configuration classes: SecurityConfig, WebConfig, and Observability for tracing purposes. 5-Participated in team meetings. 6-Set up a database instance for the user management service on Cockroach Labs. | 1 | 2 | 4 | 4 |  | 4 |  | 4 | 1-Completed the Security section in the SPP document. 2-Prepared the PowerPoint (PPT) document for presentation. 3-Configured the database connection and repositories for the user management service. 4-Created an online database instance. | 1- Same as the previous week | 1- Same as the previous week | 1-Finalized the security document and followed up with the other teams for integration. 2-Completed the implementation of endpoints for the User Management Service. | 30

## Hunter Washburne
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA, Implementation
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/07 - 05/15 | 6 | 4 | 2 | 0 - Learn how to set up SSH for GitHub. 1 - Discussed the project description and features with the team. 2 - Discussed design proposal and QA plan with the team; wrote initial QA plan draft. 5 - Participated in team meetings and group chat discussions. 6 - Set up Git. | 1 | 3 | 1 |  |  | 1 | 1 |  | initial QA plan |  |  | help with initial coding | 10