## Iteration 1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members has dropped class | 5 | 4 | 2 | 4 | team leader and all members | 6/18/2024 | Have assigned tasks to other members, as some have shared some tasks, taken on others | One person did drop: took up in-class instead - in early stages, so less actual risk - hence likelihood was 5 | Open
| add new team members | Adding other members | 1 | 4 | 2 | 20 | team leader and all members | 2024-05-30 | Not likely to occur as teams pretty set | Incorporate team member into areas that need work | Open
| Lack of motivation or responsibility | Any member that hasn't shown drive or attended | 3 | 3 | 2 | 18 | team leaders and all members | 2024-06-18 | Enquire if the work load not appropriate to their skills | Discuss openly, yet some members are hard to contact | Open
Communication | duplicate work | with collaboration across groups, aim to eliminate duplication | 4 | 3 | 2 | 12 | team leader and all members of all groups | 5/15/2024 | may be some shared responsibilties across groups | Our collaboration will improve as we spend more time | Open
| worked on wrong components | Lack of communication caused incorrect work | 2 | 3 | 1 | 12 | team leader and all members of all groups | 2024-06-18 | Seek clarity on what tasks need doing, don't focus on negative | Delegation of suitable tasks, take ownership | Open
| inconsistent work | Outside forces cause one to not have consistent hours delivered | 3 | 3 | 3 | 27 | team leader and all members | 18/6/ | Seek clarity on upcoming weeks to get buy in | May need to share out work if one/more have outside forces that are difficult to navigate | Open
Requirements | define requirements | Await feedback from other groups on Jordany proposal | 5 | 4 | 2 | 4 | team leader and all members | 5/15/2024 | Divide up responsibilities, allow for cross-pollination of ideas | To discuss at next meeting and via discord | open
| scope creep | Need to ensure effects on resources, time, and deliverables are addressed if scope of project amended | 3 | 4 | 1 | 6 | Team leader | 2024-06-12 | Should not impact beyond last week of project. Need to stay on top of any changing vision | Team discord, or zoom to flesh out issues | Open
| constant requirements changes | Many overhauls of work project, unnecessarily | 2 | 4 | 3 | 24 | Team leader and all members | 2024-06-12 | Leading in to last week, this shouldnt be an issue beyond that time | Team discord, or zoom to flesh out issues | Open
Management | improper task assignments | Should Team leader not know the skill sets of various members | 2 | 3 | 3 | 36 | Team leader | 2024-06-18 | Ask for feedback from all team of level of competency in certain delegations | One on one discussion with particular member | Open
| improper planning | As above, but also if have rogue elements within team | 3 | 4 | 4 | 24 | Team leader | 2024-06-12 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
| lack of management skills | Management of time, resources not handled well | 2 | 3 | 4 | 48 | TL and all other members | 2024-06-18 | Regular check ins and ensure proper time is given for announcing meetings and deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
Technology competence | Not familiar with the framework used | Everyone has different levels, so noting who to rely on based on skill sets | 3 | 3 | 3 | 27 | TL and all members | 2024-06-18 | Requires transparency and honest collaboration | As above, and during meetings | Open
| Not familiar with the programming language used | I believe this has been addressed by Professor and agreed on by team members | 1 | 2 | 2 | 40 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | As above and during zoom | Open
| Not familiar with unit testing | Ensuring discussion is had on who has experience in area | 3 | 4 | 4 | 24 | TL and all members | 2024-06-12 | Seek feedback and remain open to collaboration | As above and during meetings | Open
| Not familiar with Git | This has been an issue and TL has reached out for help | 5 | 2 | 2 | 8 | TL and all membes | 2024-06-12 | Await feedback from Trevor | Continue dialogue | Open
Design and implementation | Improper design | Have begun to discuss this already | 2 | 2 | 2 | 32 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | As above and during meetings | Open
| improper technology stack | Seek feedback from Trevor as we progress | 2 | 3 | 3 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Team discord, or zoom to flesh out issues
| Messy code | Be open to ask for help and ensure testing occurs regularly | 3 | 2 | 4 | 48 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | Continue dialogue
Testing | Not enough testing | May need to discuss this further as we progress into Iteration 1 | 3 | 3 | 4 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Continue dialogue
Integration and deployment | Not enough time for integration and deployment | Resource planning as we begin the larger coding sections of the work. | 4 | 2 | 3 | 24 | TL and all members | 2024-06-18 | Seek feedback and remain open to collaboration | Monday and other tools to ensure that comms are centralised and understood by all

## Iteration2
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members has dropped class | 5 | 4 | 2 | 4 | team leader and all members | 6/18/2024 | Have assigned tasks to other members, as some have shared some tasks, taken on others | One person did drop: took up in-class instead - in early stages, so less actual risk - hence likelihood was 5 And now we have not had contact with another member for around 12 days. Looks potentially like they have dropped but need clarification. | Open
| add new team members | Adding other members | 1 | 4 | 2 | 20 | team leader and all members | 2024-05-30 | Not likely to occur as teams pretty set | Incorporate team member into areas that need work | Open
| Lack of motivation or responsibility | Any member that hasn't shown drive or attended | 3 | 3 | 2 | 18 | team leaders and all members | 2024-06-18 | Enquire if the work load not appropriate to their skills | Discuss openly, yet some members are hard to contact | Open
Communication | duplicate work | with collaboration across groups, aim to eliminate duplication | 4 | 3 | 2 | 12 | team leader and all members of all groups | 5/15/2024 | may be some shared responsibilties across groups | Needs further discussion and coordination, as we did have some double up with Notificaton however JP has done up JSON formats too | Open
| worked on wrong components | Lack of communication caused incorrect work | 2 | 3 | 1 | 12 | team leader and all members of all groups | 2024-06-18 | Seek clarity on what tasks need doing, don't focus on negative | Delegation of suitable tasks, take ownership | Open
| inconsistent work | Outside forces cause one to not have consistent hours delivered | 3 | 3 | 3 | 27 | team leader and all members | 18/6/ | Seek clarity on upcoming weeks to get buy in | May need to share out work if one/more have outside forces that are difficult to navigate | Open
Requirements | define requirements | Await feedback from other groups on Jordany proposal | 5 | 4 | 2 | 4 | team leader and all members | 5/15/2024 | Divide up responsibilities, allow for cross-pollination of ideas | To discuss at next meeting and via discord | open
| scope creep | Need to ensure effects on resources, time, and deliverables are addressed if scope of project amended | 3 | 4 | 1 | 6 | Team leader | 2024-06-12 | Should not impact beyond last week of project. Need to stay on top of any changing vision | Team discord, or zoom to flesh out issues | Open
| constant requirements changes | Many overhauls of work project, unnecessarily | 2 | 4 | 3 | 24 | Team leader and all members | 2024-06-12 | Leading in to last week, this shouldnt be an issue beyond that time | Team discord, or zoom to flesh out issues | Open
Management | improper task assignments | Should Team leader not know the skill sets of various members | 2 | 3 | 3 | 36 | Team leader | 2024-06-18 | Ask for feedback from all team of level of competency in certain delegations | One on one discussion with particular member | Open
| improper planning | As above, but also if have rogue elements within team | 3 | 4 | 4 | 24 | Team leader | 2024-06-12 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
| lack of management skills | Management of time, resources not handled well | 2 | 3 | 4 | 48 | TL and all other members | 2024-06-18 | Regular check ins and ensure proper time is given for announcing meetings and deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
Technology competence | Not familiar with the framework used | Everyone has different levels, so noting who to rely on based on skill sets | 3 | 3 | 3 | 27 | TL and all members | 2024-06-18 | Requires transparency and honest collaboration | As above, and during meetings | Open
| Not familiar with the programming language used | I believe this has been addressed by Professor and agreed on by team members | 1 | 2 | 2 | 40 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | As above and during zoom | Open
| Not familiar with unit testing | Ensuring discussion is had on who has experience in area | 3 | 4 | 4 | 24 | TL and all members | 2024-06-12 | Seek feedback and remain open to collaboration | As above and during meetings | Open
| Not familiar with Git | This has been an issue and TL has reached out for help | 5 | 2 | 2 | 8 | TL and all membes | 2024-06-12 | Await feedback from Trevor | Continue dialogue | Open
Design and implementation | Improper design | Have begun to discuss this already | 2 | 2 | 2 | 32 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | As above and during meetings | Open
| improper technology stack | Seek feedback from Trevor as we progress | 2 | 3 | 3 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Team discord, or zoom to flesh out issues
| Messy code | Be open to ask for help and ensure testing occurs regularly | 3 | 2 | 4 | 48 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | Continue dialogue
Testing | Not enough testing | May need to discuss this further as we progress into Iteration 1 | 3 | 3 | 4 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Continue dialogue
Integration and deployment | Not enough time for integration and deployment | Resource planning as we begin the larger coding sections of the work. | 4 | 2 | 3 | 24 | TL and all members | 2024-06-18 | Seek feedback and remain open to collaboration | Monday and other tools to ensure that comms are centralised and understood by all

## Final
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members has dropped class | 5 | 4 | 2 | 4 | team leader and all members | 6/18/2024 | Have assigned tasks to other members, as some have shared some tasks, taken on others | One person did drop: took up in-class instead - in early stages, so less actual risk - hence likelihood was 5 And now we have not had contact with another member for around 12 days. Looks potentially like they have dropped but need clarification. We feel that we have ably moved on from that and achieved well despite the loss. | Closed
| add new team members | Adding other members | 1 | 4 | 2 | 20 | team leader and all members | 2024-05-30 | Not likely to occur as teams pretty set | Incorporate team member into areas that need work. This was not ever likely to be an issue. | Closed
| Lack of motivation or responsibility | Any member that hasn't shown drive or attended | 3 | 3 | 2 | 18 | team leaders and all members | 2024-06-18 | Enquire if the work load not appropriate to their skills | Discuss openly, yet some members are hard to contact. The 4 remaining members, despite other outside stressors all worked well. | Open
Communication | duplicate work | with collaboration across groups, aim to eliminate duplication | 4 | 3 | 2 | 12 | team leader and all members of all groups | 2024-06-18 | may be some shared responsibilties across groups | Needs further discussion and coordination, as we did have some double up with Notificaton however JP has done up JSON formats too. Define roles and responsibilities, and appointed a communication lead: Jordany. | Open
| worked on wrong components | Lack of communication caused incorrect work | 3 | 3 | 1 | 9 | team leader and all members of all groups | 2024-06-18 | Seek clarity on what tasks need doing, don't focus on negative | Delegation of suitable tasks, take ownership | Open
| inconsistent work | Outside forces cause one to not have consistent hours delivered | 2 | 3 | 3 | 36 | team leader and all members | 2024-06-18 | Seek clarity on upcoming weeks to get buy in | May need to share out work if one/more have outside forces that are difficult to navigate | Open
Requirements | define requirements | Await feedback from other groups on Jordany proposal - this obviously was accepted and Jordany juggled many different team interations, as did others. | 5 | 4 | 2 | 4 | team leader and all members | 2024-05-31 | Divide up responsibilities, allow for cross-pollination of ideas - seek out subject matter experts | To discuss at next meeting and via discord | closed
| scope creep | Need to ensure effects on resources, time, and deliverables are addressed if scope of project amended | 3 | 4 | 1 | 6 | Team leader | 2024-06-12 | Should not impact beyond last week of project. Need to stay on top of any changing vision. This did not impact us as we thought, as we stuck to the task. | Team discord, or zoom to flesh out issues | Open
| constant requirements changes | Many overhauls of work project, unnecessarily | 2 | 4 | 3 | 24 | Team leader and all members | 2024-06-12 | Leading in to last week, this shouldnt be an issue beyond that time, and that ended up being the case, as it was just more getting our head around various dependencies and new software, and new concepts. | Team discord, or zoom to flesh out issues | Closed
Management | improper task assignments | Should Team leader not know the skill sets of various members | 3 | 3 | 3 | 27 | Team leader | 2024-06-18 | Ask for feedback from all team of level of competency in certain delegations | One on one discussion with particular member, as Team Leader I know that with some huge pressures recently at work, I had not addressed this as best I could | Open
| improper planning | As above, but also if have rogue elements within team | 3 | 4 | 4 | 24 | Team leader | 2024-06-12 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Quickly shelved Monday and moved to Pivotal Tracker. This area is one that some members were better at than others, and as Team Leader I didnt get much time to get head around it. | Open
| lack of management skills | Management of time, resources not handled well - this improved over time, as we gained more efficiency. | 2 | 3 | 4 | 48 | TL and all other members | 2024-06-18 | Regular check ins and ensure proper time is given for announcing meetings and deadlines | See above re: Pivotal Tracker | Open
Technology competence | Not familiar with the framework used | Everyone has different levels, so noting who to rely on based on skill sets | 3 | 3 | 3 | 27 | TL and all members | 2024-06-18 | Requires transparency and honest collaboration | As above, and during meetings | Open
| Not familiar with the programming language used | I believe this has been addressed by Professor and agreed on by team members | 1 | 2 | 2 | 40 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | As above and during zoom | Open
| Not familiar with unit testing | Ensuring discussion is had on who has experience in area and also everyone did some reading and research on it and we held some co-coding sessions to address. | 3 | 4 | 4 | 24 | TL and all members | 2024-06-12 | Seek feedback and remain open to collaboration | As above and during meetings | Open
| Not familiar with Git | This has been an issue and TL has reached out for help - even Professor and other teams assisted, as there were some issues. | 5 | 2 | 2 | 8 | TL and all membes | 2024-06-17 | Await feedback from Trevor & Professor has been achieved and now we simply get to ensure Main is populated with all the necessary Functional code, and supporting documentation, including meeting notes, recordings, etc. | Continue dialogue | closed
Design and implementation | Improper design | Have begun to discuss this already | 2 | 2 | 2 | 32 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | As above and during meetings | Open
| improper technology stack | Seek feedback from Trevor as we progress | 2 | 3 | 3 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Team discord, or zoom to flesh out issues | Open
| Messy code | Be open to ask for help and ensure testing occurs regularly - many of us have been willing to assist with code smells and refactoring, as an ongoing function. | 3 | 2 | 4 | 48 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | Continue dialogue | Open
Testing | Not enough testing | May need to discuss this further as we progress into Iteration 1 &2, where things really started to ramp up with testing. | 3 | 3 | 4 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines. Regular analysis of code smells and remembering the DRY philosophy. | Ongoing process nearly finished now that most coding complete | Open
Integration and deployment | Not enough time for integration and deployment | Resource planning as we begin the larger coding sections of the work. Integration testing more robust and demanding of time. Those who worked on it relied on co-coding and sharing of ideas. | 4 | 2 | 3 | 24 | TL and all members | 2024-06-18 | Seek feedback and remain open to collaboration | Pivotal Tracker | Closed
Issues with Storage Space, and recordings | Ensuring that those recording the meetings have provided videos | JP had some issues due to recent change with work, moving from Virtual network to OFfice365, caused some issues on saving recordings. This has now been rectified. | 3 | 1 | 1 | 15 | TL and all members | 2024-06-15 | Ask for assistance, as everyone in the group have been willing to assist. Our last presentation is just around corner. | Zoom, Google Docs | Closed
Next Steps | What is next for this microservices project | Requires replanning, and to continuously assess and adjusst project planning. In the real world a business would now look at what we have done and via agile methods determine what is next. | 3 | 1 | 1 | 15 | TL and all members | ongoing | Regroup after a massive sprint, to give time for brain to repair! | Pivotal Tracker, Discord, Google docs etc | Closed, hypothetical