## Iteration 1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members has dropped class | 5 | 2 | 2 | 8 | team leader and all members | 6/18/2024 | Have assigned tasks to other members, as some have shared some tasks, taken on others | One person did drop: took up in-class instead - in early stages, so less actual risk - hence likelihood was 5 | Open
| add new team members | Adding other members | 1 | 4 | 2 | 20 | team leader and all members | 2024-05-30 | Not likely to occur as teams pretty set | Incorporate team member into areas that need work | Open
| Lack of motivation or responsibility | Any member that hasn't shown drive or attended | 3 | 3 | 2 | 18 | team leaders and all members | 2024-06-18 | Enquire if the work load not appropriate to their skills | Discuss openly, yet some members are hard to contact | Open
Communication | duplicate work | with collaboration across groups, aim to eliminate duplication | 4 | 3 | 2 | 12 | team leader and all members of all groups | 5/15/2024 | may be some shared responsibilties across groups | Needs further discussion and coordination, as we did have some double up with Notificaton however JP has done up JSON formats too | Open
| worked on wrong components | Lack of communication caused incorrect work | 2 | 3 | 1 | 12 | team leader and all members of all groups | 2024-06-18 | Seek clarity on what tasks need doing, don't focus on negative | Delegation of suitable tasks, take ownership | Open
| inconsistent work | Outside forces cause one to not have consistent hours delivered | 3 | 3 | 3 | 27 | team leader and all members | 18/6/ | Seek clarity on upcoming weeks to get buy in | May need to share out work if one/more have outside forces that are difficult to navigate | Open
Requirements | define requirements | Await feedback from other groups on Jordany proposal | 5 | 4 | 2 | 4 | team leader and all members | 5/15/2024 | Divide up responsibilities, allow for cross-pollination of ideas | To discuss at next meeting and via discord | open
| scope creep | Need to ensure effects on resources, time, and deliverables are addressed if scope of project amended | 3 | 4 | 1 | 6 | Team leader | 2024-06-12 | Should not impact beyond last week of project. Need to stay on top of any changing vision | Team discord, or zoom to flesh out issues | Open
| constant requirements changes | Many overhauls of work project, unnecessarily | 2 | 4 | 3 | 24 | Team leader and all members | 2024-06-12 | Leading in to last week, this shouldnt be an issue beyond that time | Team discord, or zoom to flesh out issues | Open
Management | improper task assignments | Should Team leader not know the skill sets of various members | 2 | 3 | 3 | 36 | Team leader | 2024-06-18 | Ask for feedback from all team of level of competency in certain delegations | One on one discussion with particular member | Open
| improper planning | As above, but also if have rogue elements within team | 3 | 4 | 4 | 24 | Team leader | 2024-06-12 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
| lack of management skills | Management of time, resources not handled well | 2 | 3 | 4 | 48 | TL and all other members | 2024-06-18 | Regular check ins and ensure proper time is given for announcing meetings and deadlines | Monday and other tools to ensure that communications are centralized and understood by all | Open
Technology competence | Not familiar with the framework used | Everyone has different levels, so noting who to rely on based on skill sets | 3 | 3 | 3 | 27 | TL and all members | 2024-06-18 | Requires transparency and honest collaboration | As above, and during meetings | Open
| Not familiar with the programming language used | I believe this has been addressed by Professor and agreed on by team members | 1 | 2 | 2 | 40 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | As above and during zoom | Open
| Not familiar with unit testing | Ensuring discussion is had on who has experience in area | 3 | 4 | 4 | 24 | TL and all members | 2024-06-12 | Seek feedback and remain open to collaboration | As above and during meetings | Open
| Not familiar with Git | This has been an issue and TL has reached out for help | 5 | 2 | 2 | 8 | TL and all membes | 2024-06-12 | Await feedback from Trevor | Continue dialogue | Open
Design and implementation | Improper design | Have begun to discuss this already | 2 | 2 | 2 | 32 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | As above and during meetings | Open
| improper technology stack | Seek feedback from Trevor as we progress | 2 | 3 | 3 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Team discord, or zoom to flesh out issues
| Messy code | Be open to ask for help and ensure testing occurs regularly | 3 | 2 | 4 | 48 | TL and all members | 2024-06-18 | Be open to asking for assistance and guidance | Continue dialogue
Testing | Not enough testing | May need to discuss this further as we progress into Iteration 1 | 3 | 3 | 4 | 36 | TL and all members | 2024-06-18 | Need to stay on top of various elements and check in at least 2x / week on delivery and meeting deadlines | Continue dialogue
Integration and deployment | Not enough time for integration and deployment | Resource planning as we begin the larger coding sections of the work. | 4 | 2 | 3 | 24 | TL and all members | 2024-06-18 | Seek feedback and remain open to collaboration | Monday and other tools to ensure that comms are centralised and understood by all